Melbourne Institute of Technology

School of Information Technology and Engineering

MDA691 — Project Management and Research Methods

Trimester 2, 2026  ·  Assignment 2 — Individual Report (Weeks 5–8)

Real-Time Data with Agentic AI for Industrial Predictive Maintenance (PdM)

| Student name | Asmita Pandey |
| --- | --- |
| Student ID | MIT250081 |
| Primary role (Weeks 5–8) | Requirements and quality lead; client evidence, risks, traceability, literature |
| Industry client | eLabtronics / runlinc — Miroslav Kostecki |
| Group report sections owned | §4 requirements; §9 risks; traceability; Appendix I/III; WBS 4 |

1. Participation and contribution (Weeks 5–8)

During Weeks 5–8 the group converted the Assignment 1b concept into an Assignment 2 project plan and intermediate design. My theme was requirements quality, client engagement evidence, risk management, and critical literature synthesis. I was accountable for refined FR/NFR tables, the lab-versus-factory scope statement, traceability matrix, risk register, client meeting documentation, Appendix I client details, Appendix III response to Assignment 1 feedback, and coordination of literature quality (WBS Package 4).

Reworked requirements so team E32W / 37-in-1 lab data is in scope and client factory/plant telemetry is out of scope.

Built the client engagement evidence table (meetings 10, 17, 24 August 2026) with outcomes and artefacts.

Aligned four RQs to measurable objectives and success criteria after Assignment 1b feedback on RQ4.

Maintained the risk register (R1–R6) with owners and mitigations used in §9.

Prepared Appendix III itemised responses mapping marker feedback to Assignment 2 sections.

Contributed ten annotated Appendix II sources on PdM surveys, XAI/trust, and Industry 4.0 context.

Attended client meetings 10, 17 and 24 August 2026 and 7 September; recorded scope and documentation guidance.

Reviewed agent authority / HITL wording with Amit so safety claims stay consistent with the dual-path design.

Checked that FR/NFR tables, RQs, and objectives remain consistent across §§2, 4 and 7 before report freeze.

Supported Appendix I client confirmation fields (hardware supplied, data scope, contact) for submission completeness.

2. Attendance

| Week | Tutorial / supervision | Client / extra |
| --- | --- | --- |
| 5 | Present | — |
| 6 | Present | Client meeting 17/08/2026 (runlinc hotspot setup) |
| 7 | Present | Client meeting 24/08/2026 (hardware; Projects 14/15) |
| 8 | Present | Supervisor feedback; A2 report preparation |

3. Self-evaluation

I met my Week 5–8 responsibilities by turning supervisor feedback into checklist actions: clearer RQs, measurable objectives, client evidence, and a critical literature gap statement. That improved submission quality beyond a generic Industry 4.0 write-up. I could tighten weekly minutes templates earlier so evidence capture is automatic. After the 7 September meeting I also captured documentation and presentation guidance so the group report and Appendix II stay aligned for Moodle upload. Overall I contributed consistently to requirements, risks, client documentation, literature, and report coherence.

4. Reflective journal (DEEP)

| Stage | Reflection |
| --- | --- |
| Describe How effectively did you work in the group and what was your role? | I worked as Requirements and quality lead. I coordinated evidence across members without taking over their technical WBS packages, and I checked that architecture, RQs, objectives, and risks told one consistent project story. |
| Explore List at least 2 valuable contributions and why they mattered. | (1) Client meeting evidence + lab-data scope clarification — directly answered Assignment 1b feedback and prevented factory-data misunderstandings. (2) RQ–objective mapping and Appendix III feedback matrix — made Assignment 2 improvements auditable for markers. |
| Evaluate How do you justify your key contributions? | MDA691 marks planning quality and response to feedback. Without documented meetings, measurable objectives, and risk owners, a strong technical idea still loses marks. My contributions protect that planning layer. |
| Plan What did you learn and how will you improve next? | I learned to treat feedback tables as living project controls. Next I will keep requirements/traceability updated as edge and RUL interfaces freeze, and prepare evaluation checklists for Weeks 12–16 scenario testing. |

5. Peer evaluation

Scale: 1 = poor, 5 = excellent. Rate other members only.

| Criteria | Amit | Subala | Pavan |
| --- | --- | --- | --- |
| Attends group meetings regularly and arrives on time. | 5 | 5 | 5 |
| Contributes meaningfully to group discussions. | 5 | 5 | 5 |
| Completes group assignments on time. | 5 | 5 | 4 |
| Prepares work in a quality manner. | 5 | 5 | 5 |
| Demonstrates a cooperative and supportive attitude. | 5 | 5 | 5 |
| Contributes significantly to the success of the project. | 5 | 5 | 5 |
| Short feedback | Strong agent design and report integration; architecture Figure 1 improved clarity. | Dependable hardware leadership; clear GPIO/reflex planning and lab evidence. | Good analytics/schedule control; Gantt and RUL workflow support the plan. |

Signature: Asmita Pandey

Date: 13 September 2026